## Sheet1
Main Use Case | Sub Use Case | Status | Comment | Assignee
1.Rule Authoring
1.1 | Duplicate rule variable/label creation | In progress |  | Santhosh(Context menu)
1.2 | Special let case dropdown | yet to start |  | Santhosh(Context menu)
1.3 | Go to label | yet to start |  | Santhosh(Context menu)
1.4 | Basic Services Handling | completed |  | Santhosh(Context menu)
1.5 | Duplicate rule variable/label creation | completed |  | mani
1.6 | Go to label | completed |  | mani
1.7 | Commented lines | In progress |  | mani
1.8 | custom line numbers | yet to start |  | mani
2.Rule Definition Save
2.1 | Object Construction | completed |  | Arun
2.2 | Add /Remove Statement | In progress |  | Arun
2.3 | Nested Rule adding | completed |  | Arun
3.Rule Rendering (Saved Rule)
4.Rule Validate | Validating rule | completed |  | Guna
| Compiling rule | In progress |  | Guna
5.Rule Format
5.1 | Formating internal/external services and Rules | completed |  | manish
5.2 | Formating IF service | completed |  | raji
5.3 | Formating services/Rules in IF, THEN, OTHERWISE block | in progress |  | manish
5.4 | Formating nested IF Service | in progress |  | raji
5.5 | Formatingservices/rules in nested IF blocks | yet to start |  | manish
5.6 | Formating nested IF blocks in THEN,OTHERWISE Block | yet to start |  | raji
5.7 | Adding empty line after each flow control services | yet to start |  | manish
6.Group Creation in JSTree
6.1 | UI design | completed |  | Arun
6.2 | server code logic | completed |  | Arun
6.3 | DB insertion | completed |  | Arun
7.Rule Creation in JSTree
7.1 | UI page design | completed |  | Arun
7.2 | server level code logic | completed |  | Arun
7.3 | DB insertion | completed |  | Arun